## Tasks
Module/Learning/Documentation | User Story | User Story Description | Estimated Effort(hrs) | Spent Effort (hrs) | To Do Efforts | Assigned To | Start Date | End Date | Status | Remarks
Learning | Angular Basics | Setup,AppModule and Compomnent Declaration | 3 | 3 |  | Paridhi | 2023-07-16 | 2023-07-16 | Done
Learning | Components and Data Binding | Property and event binding,Component Lifecycle,View Child | 5 | 4.5 |  | Paridhi | 2023-07-17 | 2023-07-17 | Done
Learning | Services | Need Services,Create Services | 4 | 4 |  | Paridhi | 2023-07-18 | 2023-07-18 | Done
Learning | Routing | Router,Navigation Paths,Query Parameters and Fragments,Nested Route,Wild Card Routes,Redirection,Lazy Loading | 8 | 9 |  | Paridhi | 2023-07-19 | 2023-07-20 | Done
Learning | Observables | Observables,Custom Observable | 5 | 5 |  | Paridhi | 2023-07-21 | 2023-07-22 | Done
Learning | Pipes | Pipes,Creating Custom Pipes | 4 | 4 |  | Paridhi | 2023-07-23 | 2023-07-23 | Done
Learning | Template Driven Forms | Template-Driven Creation and Validation | 7 | 8 |  | Paridhi | 2023-07-24 | 2023-07-24 | Done
Learning | Reactive Forms | Reactive Forms Creation and Validation | 7 | 6.5 |  | Paridhi | 2023-07-25 | 2023-07-25 | Done
Learning | Http Requests | Get,Post,Put,Delete,Patch | 8 | 8 |  | Paridhi | 2023-07-26 | 2023-07-28 | Done
Learning | Authentication | Login,Logout,Auth Guard | 11 | 11 |  | Paridhi | 2023-07-28 | 2023-07-30 | Done
Learning | Modules | Featured Module,Shared Module,Lazy Loading | 5 | 5 |  | Paridhi | 2023-07-31 | 2023-07-31 | Done
Documentation | Balsamiq | UI Design of project | 6 | 6 |  | Paridhi | 2023-08-01 | 2023-08-01 | Done
Documentation | Developer Guide | General and Angular Coding Guidelines | 4 | 3.5 |  | Paridhi | 2023-08-02 | 2023-08-02 | Done
Documentation | Test Cases Creation-V1 | Write test cases for Auth and Team members modules |  |  |  | Paridhi | 2023-08-03 |  | Done
Documentation | Project Report | Project Report | 3 |  |  | Paridhi | 2023-08-04
Authentication & Authorization | Login page desining | 1- The title of the login page should be '' 2- There should be two input fields 'Email' and 'Password' 3- there should be a login button 4-validation should be in red color | 5 | 5 |  | Paridhi | 2023-08-05 | 2023-08-05 | Done
Authentication & Authorization | Authenticate User | 1. After successfully entering the correct login credentials, the authenticated user will be redirected to the main page. | 6 | 6 |  | Paridhi | 2023-08-06 | 2023-08-06 | Done
Main Page | Header | 1.After login,There will be a navbar. 2. In the left of the navbar there should be the name of project and in the middle there will be the modules name 3. At right, there should be the login person email and role 4. At the end,there should be a logout button | 4 | 3.5 |  | Paridhi | 2023-08-07 | 2023-08-07 | Done
Team Member | List Team Members | 1.There will be an employee table in which the employee data is displayed. The field will be EmpId,Name,Grade,Designation,Projects,Skills,Location,ContactNo,Actions 2.There will be pagination in which user can select the number of employee data displayed. 3. User can sort the values also 4. there will be a search option in which the user can search within the employee table so that he is able to directly search the employee | 5 | 5 |  | Paridhi | 2023-08-08 | 2023-08-08 | Done
Team Member | Add new Employee | 1. There should be an add button which is only visible to admin only. 2. On Click on add button a popup open which contains all the fields of the employee data. 3. Admin can enter the values in the fields. 4. there will be a save button in the bottom 5. Onclick on save button,a new row with the values will be added | 2 | 2.5 |  | Paridhi | 2023-08-09 | 2023-08-09 | Done
Team Member | Update Employee | 1. There will be an edit button in every row 2. Edit button will be enabled for manager and admin and for the employee who login can edit his details only and rest of the employee button will be disabled 3. Onclick on edit button, a dialog box appears which contains the field and values of the particular employee 4 Employee Id will be disabled so that nobody can change it 5. In the dialog box,the user will be able to edit the details and on click on save it will be reflected in the employee table | 5 | 5 |  | Paridhi | 2023-08-10 | 2023-08-10 | Done
Team Member | Upload Employee List | 1. Add upload button 2. On click a dialog box open where there is an option of choose file and after choose file there is an upload button 3.There are records added section also in which the number of records that are uploaded is displayed 4. On click on upload button the records uploaded will be added in the employee table | 3 | 3 |  | Paridhi | 2023-08-11 | 2023-08-11 | Done
Team Member | Download Employee List | 1.Add a download button 2. Onclick on download the employee list will be downloaded. | 1 | 1 |  | Paridhi | 2023-08-11 | 2023-08-11 | Done
Team Member | Logout | 1 Onclick on logout user will logout and redirect to login page | 1 | 1.5 |  | Paridhi | 2023-08-12 | 2023-08-12 | Done
Training | Routing,List Training Data | 1. On click on training in header user will directed to training page 2. There will be table in which training data is displayed.The field will be Name, TrainingTitle, TrainingType, Mode, PlannedDate, StartDate, EndDate, Status, Actions | 3 | 3 |  | Paridhi | 2023-08-13 | 2023-08-13 | Done
Training | Nominate Training to team members | 1.Add button added 2. On click on add button, a dialog box open which have the field in the table and have a nominate field also in which admin and manager can nominate team member for training. 3.Add button will be displayed to manager and admin only. | 6 | 6.5 |  | Paridhi | 2023-08-14 | 2023-08-14 | Done
Training | Edit Training List | 1. On click on edit button, a dialog box appear in which it have the same field with values as in the table. 2. Nominate will be disabled so that nobody can change it. 3. Edit the field and on click on Save it will display in the table | 3 | 3 |  | Paridhi | 2023-08-15 | 2023-08-15 | Done
Training | Add Download Button | On Click on download button, the list will be downloaded | 1 | 1 |  | Paridhi | 2023-08-15 | 2023-08-15 | Done
Dashboard | Dashboard Crads | 1.Add 4 cards in dashboard 2. In the first card,total team members are thee. 3. In the second card,total projects are there. 4. In the third card,WFO,WFH,Leave are there 5. In the fourth card, total trainings are there | 1 | 1 |  | Paridhi | 2023-08-16 | 2023-08-15 | Done
Dashboard | Bargraph and PieChart | Bargraph will represent the designation and piechart will represent the skills and they are in hard coded form | 3 | 3.5 |  | Paridhi | 2023-08-16 | 2023-08-16 | Done
Demo with Mentor |  |  | 1 | 1 |  | Paridhi | 2023-08-16 | 2023-08-16 | Done
Dashboard | Cards | 1. 4 cards,in the first card there are number of total employees. 2. In the second card, there are total projects. 3. In the third card, there is WFO/WFH/Leave 4. In the fourth card there are total trainings today and in the week. | 1 | 1 |  | Paridhi | 2023-08-17 | 2023-08-17 | Done
Dashboard | Barchart and PieChart | 1.There is barchart in which distribution of team-members on the basis of grade are there 2. There is piechart in which distribution of employees on the basis of skills are there | 4 | 4 |  | Paridhi | 2023-08-18 | 2023-08-18 | Done
WFO/Leave | Designing of the page | 1. In this first design the table and add a datepicker where the month and year is selected. 2. Then add a WFO preferences in which there are Mon,Tue,Wed,Thu,Fri options to allow tea m members to select WFO day 3.Then design the table | 2 | 2 |  | Paridhi | 2023-08-19 | 2023-08-19 | Done
WFO/Leave | Add WFO prefrences functionality | 1. If team member login, he will be able to see the WFO preferences for current month only one time, after click on apply it disappear. 2.Team member will not be able to see the WFO prefrences for previous month. 3. On click on apply data will be displayed for whole month in which WFO days are of Wfo preferences and saturday sunday is displayed by smile and rest are WFH | 3 | 3 |  | Paridhi | 2023-08-19 | 2023-08-19 | Done
WFO/Leave | WFO/WFH/Leave | Team member will only be able to see only his attendance If admin or manager login they will be able to see all team member attendance. User will be able to change forecast on click on cell of current date and above current date but admin and manager are allowed to change forecast of any date | 5 | 5.5 |  | Paridhi | 2023-08-20 | 2023-08-20 | Done

## Issues
IssueId | Description | Priority | Page/Section | Logged Date | Completion Date | AssignedTo | Status | Remarks
I0001 | Login email validations are not working | High | Login | 2023-08-05 | 2023-08-06 | Paridhi | Done
10002 | In add button after adding new employee it is not displayed in the employee table | High | Team Member | 2023-08-09 | 2023-08-09 | Paridhi | Done
10003 | as records added and on click on upload button records are not visible in table | High | Team Member | 2023-08-10 | 2023-08-10 | Paridhi | Done
10005 | Add,Upload,Download button color is not good | Low | Team Member |  |  | Paridhi | Done
10006 | Router Active is not working | High | Navbar | 2023-08-07 | 2023-08-07 | Paridhi | Done
10007 | EmpId should be disabled so that no one can change it in edit button | Low | Team Member | 2023-08-10 | 2023-08-11 | Paridhi | Done
10008 | Edit data is not displayed | High | Training | 2023-08-14 | 2023-08-14 | Paridhi | Done
10009 | in Add training fields are not shown correctly | High | Training | 2023-08-15 | 2023-08-15 | Paridhi | Done
10010 | charts are not displaying data | High | Dashboard | 2023-08-17 | 2023-08-17 | Paridhi | Done
10011 | TO,TH,TL are not displayed correctly | High | WFO/Leave | 2023-08-19 | 2023-08-19 | Paridhi | Done
10012 | Tooltip is not correct | High | Training | 2023-08-20 | 2023-08-20 | Paridhi | Done
10013 | UI of edit is not correct | Low | Team Member | 2023-08-22 | 2023-08-22 | Paridhi | Done
10014 | On click on Team Service it will redirect to dashboard page | High | Navbar | 2023-08-22 | 2023-08-22 | Paridhi | Done